PROJECT CHARTER

Household Budget Optimization Initiative

| Field | Detail |
| --- | --- |
| Project Sponsor / Owner | Dhayanithi Ramaraj |
| Project Manager | Dhayanithi Ramaraj |
| Stakeholders | Household members (immediate family) |
| Start Date | 6 January 2026 |
| Target Completion Date | 28 March 2026 (12-week cycle) |
| Document Status | Approved |

# 1. Purpose and Background

Household discretionary spending had grown inconsistent month to month, with no shared visibility into where money was going or why. This project applies standard project management practice, a charter, a defined scope, a tracked budget, and a formal closeout, to bring structure to household finances and produce a measurable, repeatable process.

# 2. Objectives and Success Metrics

- Reduce average monthly discretionary spend by 15% within the 12-week project window.

- Establish a single source of truth for income, fixed costs, and variable spend, updated weekly.

- Identify and eliminate at least 3 recurring costs with no corresponding value (unused subscriptions, avoidable fees, duplicate services).

- Build a repeatable monthly review process the household can sustain after the project closes.

# 3. Scope

## In Scope

- Tracking of all household income and expense categories on a weekly cadence.

- Variance analysis comparing budgeted vs. actual spend by category.

- A dashboard summarizing spend trends and savings progress.

- A final closeout report comparing outcomes against the objectives above.

## Out of Scope

- Investment planning, tax strategy, and long-term retirement planning.

- Debt restructuring or refinancing decisions.

# 4. Timeline and Milestones

| Milestone | Target Date | Deliverable |
| --- | --- | --- |
| Charter approved, baseline budget set | 6 Jan 2026 | Signed charter, Week 0 baseline in tracker |
| Sprint 1 review (Weeks 1-4) | 3 Feb 2026 | Variance report, early course correction |
| Sprint 2 review (Weeks 5-8) | 3 Mar 2026 | Updated variance report, subscription audit |
| Project closeout (Weeks 9-12) | 28 Mar 2026 | Final report, savings achieved vs. target |

# 5. Budget and Resources

No external budget is allocated to this project; the deliverable is a change in spending behavior, tracked in a shared spreadsheet. Resources required: 30-45 minutes weekly for data entry and review, one household member designated as data owner.

# 6. Risks and Constraints

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| Irregular or unexpected expenses distort variance data | Medium | Maintain a separate one-off expense category, excluded from recurring variance calculations |
| Inconsistent weekly data entry | Medium | Fixed weekly reminder; data owner accountable for entry |
| Household resistance to reduced discretionary spend | Low | Set targets collaboratively; review progress together, not unilaterally |

# 7. Approval

This charter was reviewed and approved by all identified stakeholders prior to project start.

Prepared by: Dhayanithi Ramaraj

Date: 6 January 2026